## Belcher Pk.& Cochato Camp House
| Town of Randolph: Priority for ADA Transition Plan - Town Parks and Playgrounds | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. -Does not include costs for accessibility renovation to outdoor areas or handrails. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Randolph
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Belcher Park and Cochato Camp House | A. Exterior Access Route | N. Accessible route not provided | Shed | Ext. |  | Priority 1 | Program Access | If the shed is used by members of the public, ensure that it is located on an accessible route. | 1 | 0
2 | Belcher Park and Cochato Camp House | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided N. Sign not provided | Parking | Ext. |  | Priority 1 | Program Access | Provide a van accessible parking space with a marked access aisle that is at least 96" wide. Provide a sign with the International Symbol of Accessibility (ISA) with the bottom of the sign 60" min. above the ground. Add the designation "Van Accessible" to the sign located at the van accessible space. Ensure the slope at the parking space and access aisle is no greater than 2.00 % (1:50) in all directions. | 1 | 0
3 | Belcher Park and Cochato Camp House | E. Exterior Ramp | T. Not maintained in operable working condition | Ramp to Side Entrance | Ext. |  | Priority 1 | Program Access | Ensure the ramp is maintained in operable working condition. Provide a compliant ramp 48" wide min. with handrails, landings and edge protection. | 1 | 0
4 | Belcher Park and Cochato Camp House | G. Entrance | C. Directional sign to accessible entrance not provided | Main Entrance | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
5 | Belcher Park and Cochato Camp House | A. Means of Egress | B. Tactile exit sign not provided | Egress to Ramp |  |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
6 | Belcher Park and Cochato Camp House | A. Means of Egress | K. Threshold > 1/2" high B. Tactile exit sign not provided P. Directional sign to accessible emergency exit not provided | Main Egress to Stairs | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. Alter the threshold to be 1/2" high max. | 1 | 614
7 | Belcher Park and Cochato Camp House | C. Doors, Doorways, & Gates | K. Threshold > 1/2" high | Shed | Ext. |  | Priority 3 | Additional Access | If the shed is used by members of the public, alter the threshold to be 1/2" high max. | 1 | 150
8 | Belcher Park and Cochato Camp House | C. Doors, Doorways, & Gates | L. Hardware not operable with a closed fist A. Clear width at door < 32" | Toilet Room Door | 1 |  | Priority 1 | Program Access | Widen the door so that there is 32" min. clear width. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. Note: Cost to widen door and replace door hardware is included in the cost for a new accessible all gender single-user toilet room shown in ID #14. | 1 | 0
9 | Belcher Park and Cochato Camp House | E. Stairways | D. Handrails do not extend 12" from stairs E. Handrails have non-compliant cross section | Main Entrance | Ext. |  | Priority 3 | Additional Access | Bottom: Ensure handrails extend to one tread depth beyond the last riser. Provide handrails with 1 1/4" - 2" circular cross sections. | 1 | 0
10 | Belcher Park and Cochato Camp House | M. Dining or Work Surfaces | A. Not on a accessible route C. Knee or toe clearance not provided | Picnic Pavilion by Pond | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the picnic pavilion Provide at least one dining surface (picnic table) with 27" min. knee and toe clearance. | 1 | 0
11 | Belcher Park and Cochato Camp House | M. Dining or Work Surfaces | B. At least one or 5% accessible tables not provided C. Knee or toe clearance not provided | Picnic Pavilion by Parking | Ext. |  | Priority 1 | Program Access | If these picnic tables are used by members of the public, ensure at least one picnic table is accessible and that it is located on an accessible route. | 1 | 0
12 | Belcher Park and Cochato Camp House | U. Kitchens and Kitchenettes | A. Knee/toe clearance not provided at sink | Kitchen | 1 |  | Priority 1 | Program Access | Provide a sink with knee and toe clearance positioned for a forward approach. | 1 | 3094
13 | Belcher Park and Cochato Camp House | U. Kitchens and Kitchenettes | D. Knee/toe clearance not provided at cooktop E. Control panels at cooktop not at front H. Knee/toe clearance not provided at countertop M. Wall oven type not provided | Kitchen | 1 |  | Priority 1 | Program Access | Provide a cooktop with knee and toe clearance positioned for a forward approach. Provide a cooktop with controls that do not require reaching across burners. Ensure knee and toe clearance are provided at the countertop (if forward approach). Ensure that a wall type oven is provided. Note: Both bottom and side-hinged wall ovens require a retractable "bread board" type shelf. | 1 | 3200
14 | Belcher Park and Cochato Camp House | A. Overall Access | B. Turning space not provided C. Accessible plumbing fixtures or stalls not provided | Toilet Room | 1 |  | Priority 1 | Program Access | Renovate to provide an accessible single-user toilet room. | 1 | 24604
15 | Belcher Park and Cochato Camp House | B. Play Areas | A. Accessible route not provided to playground | Playground Entrance | 1 |  | Priority 1 | Program Access | Install an accessible route to the playground. | 1 | 0
16 | Belcher Park and Cochato Camp House | B. Play Areas | A. Accessible route not provided to playground B. Accessible route not provided around playground C. Accessible route not provided to play components | Playground | Ext. |  | Priority 1 | Program Access | Install an accessible route around the playground. Provide a compliant impact-attenuating surface to and around the play components. | 1 | 0
17 | Belcher Park and Cochato Camp House | D. Court | C. Court is not connected to an accessible route | Basketball Court | Ext. |  | Priority 1 | Program Access | Provide a stable, firm and slip resistant accessible route to the basketball court. | 1 | 0
18 | Belcher Park and Cochato Camp House | Exterior Stairs |  | Main Entrance | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing contrasting colored strips on the exterior stairs. | 1 | 0