## Imagination Station
| Town of Randolph: Priority for ADA Transition Plan - Town Parks and Playgrounds | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. -Does not include costs for accessibility renovation to outdoor areas or handrails. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Randolph
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Imagination Station Playground | F. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces O. Sign does not have the designation "Van Accessible" P. Sign bottom < 60" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Add the designation "Van Accessible" to the sign located at the van accessible space. At both accessible parking spaces, locate signs with the bottom of the signs 60" min. above the ground measured to the bottom of the sign and 96" max. measured to the top of the sign. Re-stripe faded parking space lines at accessible spaces as needed. | 1 | 0
2 | Imagination Station Playground | J. Picnic Tables | B. Number of accessible seating spaces G. Toe or knee clearance at table not provided | Inside Playground | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath. | 1 | 0
3 | Imagination Station Playground | J. Picnic Tables | B. Number of accessible seating spaces G. Toe or knee clearance at table not provided H. Picnic table not on an accessible route | Picnic Tables by Gazebo | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath. Ensure that the picnic table is connected to an accessible route. | 4 | 0
4 | Imagination Station Playground | J. Picnic Tables | B. Number of accessible seating spaces G. Toe or knee clearance at table not provided H. Picnic table not on an accessible route | By Playground | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath. Ensure that the picnic table is connected to an accessible route. | 1 | 0
5 | Imagination Station Playground | L. Benches | A. No accessible route to one bench in this area | Bench in Playground Older Area | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
6 | Imagination Station Playground | L. Benches | A. No accessible route to one bench in this area | Bench by Gazebo | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
7 | Imagination Station Playground | B. Play Areas | A. Accessible route not provided around playground B. Accessible route not provided at play components | Playground Older Age Area | Ext. |  | Priority 1 | Program Access | Install an accessible route to and around the playground. Provide a compliant impact-attenuating surface under and around the play components. | 1 | 0
8 | Imagination Station Playground | B. Play Areas | B. Accessible route not provided at play components | Playground Tot Area | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface under and around the play components. | 1 | 0
9 | Imagination Station Playground | Benches |  | Bench by Gazebo | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" min. by 48" min. stable, firm and slip-resistant surface adjacent to at least one (1) bench in the park at each location where benches are provided. | 1 | 0