## South Main Station Playground
| Town of Randolph: Priority for ADA Transition Plan - Town Parks and Playgrounds | [9 empty] | **IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. - There is no cost noted when it's presumed to be a maintenance issue. -Does not include costs for accessibility renovation to outdoor areas or handrails. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Randolph
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | South Main Station Playground | C. Doors, Doorways, & Gates | M. Gate requires excessive opening force. | Basketball Court | Ext. |  | Priority 3 | Additional Access | Adjust gate to require no more that 15 pounds of opening force. | 1 | 0
2 | South Main Station Playground | E. Stairways | D. Handrails do not extend 12" from stairs | Basketball Court | Ext. |  | Priority 3 | Additional Access | Bottom: Ensure handrails extend to one tread depth beyond the last riser. | 1 | 0
3 | South Main Station Playground | T. Exterior Benches | A. No accessible route to one bench in area | Playground | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in this area. | 1 | 0
4 | South Main Station Playground | B. Play Areas | B. Accessible route not provided around playground | Playground | Ext. |  | Priority 1 | Program Access | Provide a 48" wide min. accessible route around the perimeter of the play area inside the fence. | 1 | 0
5 | South Main Station Playground | B. Play Areas | C. Accessible route not provided to play components | Playground | Ext. |  | Priority 1 | Program Access | Provide a compliant impact-attenuating surface to and around the play components. | 1 | 0
6 | South Main Station Playground | Parking by Basketball Court |  | Basketball Court | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a van accessible parking space near the accessible entrance to the basketball court. | 1 | 0